## Sheet1
Task | Modules | Hour | Start Date | End Date | Responsibility
Iteration 1
Add Links | Manage Link | 4 | 31/10/13 | 2013-01-11 | Zafir
View Links | Manage Link | 4 | 2013-02-11 | 2013-03-11 | Zafir
Edit Links | Manage Link | 8 | 2013-04-11 | 2013-07-11 | Zafir
Delete Links | Manage Link | 8 | 2013-08-11 | 2013-10-11 | Zafir
Fill Links in Manage Page | Manage Content | 8 | 2013-10-11 | 2013-10-11 | Zafir
Create Page Widgets as per control | Manage Content | 8 | 2013-04-11 | 2013-05-11 | Rasmikant
Theming and Fill CMS Widgets | Manage Content | 6 | 2013-06-11 | 2013-07-11 | Rasmikant
Theming and Fill Feedback Widgets | Manage Content | 6 | 2013-08-11 | 2013-09-11 | Rasmikant
Theming and Fill Contact Widgets | Manage Content | 6 | 2013-09-11 | 2013-09-11 | Rasmikant
Theming and Fill Product Widgets | Manage Content | 6 | 2013-10-11 | 2013-10-11 | Rasmikant
Add/Update CMS Content | CMS | 8 | 2013-10-11 | 2013-10-11 | Rasmikant
Iteration 2
Config Email | Feedback | 6
View Feedback | Feedback | 8
Search Feedback | Feedback | 6
Delete Feedback | Feedback | 4
Reponse Feedback | Feedback | 6
Add Contact | Contact | 6
View Contact | Contact | 6
Add/Update Category | eCommerce | 4
View/Delete Category | eCommerce | 6
Add/Update Subcatagory | eCommerce | 4
View/Delete Sub Category | eCommerce | 6
Add/Update Item | eCommerce | 12
View/Delete Item | eCommerce | 8
View Enquiries | eCommerce | 8
Reponse Enquires | eCommerce | 6